## UAT-PS
UAT PLAN-PS
Sr no | Title | SAP S/4HANA Cloud apps name | Integration | Ownership | From Date | To Date | Time
| Business Process Understanding Workshop | [5 empty] | (Ethiopia Time)
1 | Master Data |  |  | Haile Belay/ Shashank/Divye | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
2 | Create Project | Project Control - Enterprise Projects |  | Haile Belay/ Shashank/Divye | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
3 | Edit Project | Project Control - Enterprise Projects |  | Haile Belay/ Shashank/Divye | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
4 | Create Work Breakdown Structure(WBS Element) | Project Control - Enterprise Projects |  | Haile Belay/ Shashank/Divye | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
5 | Project plan and Budgeting Process |  |  | Haile Belay/Jai Gautam | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
6 | Import Financial Data | Manage Budget Documents - | PS-FI | Haile Belay/Jai Gautam | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
7 | Create Milestone |  |  | Haile Belay/Jai Gautam | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
8 | Project Demand |  |  | Haile Belay/Jai Gautam | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
9 | Material Demand | Manage Project Demand | PS-MM | Melisew/Deepanshu | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
10 | Actual Costing in Projects |  |  | Haile Belay/Jai Gautam | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
11 | Release Projects/Project Parts | Manage Cost Center Budgets |  | Haile Belay/Jai Gautam | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
12 | Billing customer projects |  | PS-FI | Haile Belay/Jai Gautam | 25.01.2025 | 25.01.2025 | 9:00 AM- 4:00 PM
13 | Period end Activities in Projects | [5 empty] | 9:00 AM- 4:00 PM
14 | Complete Project Parts and Project | Project Control - Enterprise Projects |  | Haile Belay/ Shashank/Divye | 25.01.2025 | 25.01.2025 | 9:00 AM- 4:00 PM
15 | Reporting in Project system |  |  | Haile Belay/ Shashank/Divye | 28.01.2025 | 28.01.2025 | 9:00 AM- 4:00 PM
16 | Monitor Projects | Monitor Projects |  | Haile Belay/ Shashank/Divye | 28.01.2025 | 28.01.2025 | 9:00 AM- 4:00 PM
17 | Project Cost Report - Plan/Actua | Project Budget Report |  | Haile Belay/ Shashank/Divye | 28.01.2025 | 28.01.2025 | 9:00 AM- 4:00 PM
18 | Project Budget Report | Manage Project Procurement |  | Haile Belay/ Shashank/Divye | 28.01.2025 | 28.01.2025 | 9:00 AM- 4:00 PM
19 | Manage Project Procurement | Plan/Actual |  | Haile Belay/ Shashank/Divye | 28.01.2025 | 28.01.2025 | 9:00 AM- 4:00 PM
20 | Project Briefs |  |  | Haile Belay/ Shashank/Divye | 28.01.2025 | 28.01.2025 | 9:00 AM- 4:00 PM
21 | Project Profitability |  |  | Haile Belay/ Shashank/Divye | 28.01.2025 | 28.01.2025 | 9:00 AM- 4:00 PM

## Controlling
UAT PLAN-CO
Sr no | Title | SAP S/4HANA Cloud apps name | Integration | Ownership | From Date | To Date | Time
| Business Process Understanding Workshop | [5 empty] | (Ethiopia Time)
Master Data
1 | Create Profit Center | Manage Profit Centers |  | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
2 | Change Profit Center | Manage Profit Centers |  | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
3 | Create Cost Center | Manage Cost Centers |  | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
4 | Create Cost Center Group | Manage Cost Center Groups |  | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
5 | Create Cost Element Group | Manage Cost Element Groups |  | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
6 | Create Activity Type | Manage Activity Types |  | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
7 | Create SKF | Manage StatIstical Key Figures |  | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
Cost Centerplan and Budgeting Process
8 | Import Cost Center Financial Plan Data | Import Financial Plan Data | CO-FI | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
9 | Import Cost Center Budget Data | Import Financial Plan Data | CO-FI | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
10 | Manage Cost Center Budgets | Manage Cost Center Budgets | CO-FI | Haile Belay/ Jai | 23.01.2025 | 23.01.2025 | 9:00 AM- 4:00 PM
11 | Import SKF Plan Data | Import Statstical key Figures l Plan Data | CO-FI | Haile Belay/ Jai | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
12 | Manage Activity type plan cost Rates | Manage cost rates plan | CO-FI | Haile Belay/ Jai | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
Actual Costing and Period end Processes
13 | Record Cost with Cost Center | Post General Journal Entries | CO-FI | Haile Belay/ Jai | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
14 | Create Purchase Order | Create Purchase Order Advanced | CO-FI | Haile Belay/ Jai | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
15 | Reassign costs/Revenues | Reassign costs and Revenues | CO-FI | Haile Belay/ Jai | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
16 | Repost Costs/Revenues line items | Repost line items cost accounting | CO-FI | Haile Belay/ Jai | 24.01.2025 | 24.01.2025 | 9:00 AM- 4:00 PM
17 | Manage Overhead cost Allocations | Manage Allocations | CO-FI | Haile Belay/ Jai | 27.01.2025 | 27.01.2025 | 9:00 AM- 4:00 PM
18 | Run Allocations | Run Allocations | CO-FI | Haile Belay/ Jai | 27.01.2025 | 27.01.2025 | 9:00 AM- 4:00 PM
| Reporting in Conytrolling |  |  | Haile Belay/ Jai | 27.01.2025 | 27.01.2025 | 9:00 AM- 4:00 PM
19 | Display Line item Cost Accounting | Display Line item Cost Accounting |  | Haile Belay/ Jai | 27.01.2025 | 27.01.2025 | 9:00 AM- 4:00 PM
20 | Cost center Plan/Actual/commitment | Plan/Actual/Committed |  | Haile Belay/ Jai | 27.01.2025 | 27.01.2025 | 9:00 AM- 4:00 PM
21 | Cost center review booklet | Cost center review booklet |  | Haile Belay/ Jai | 27.01.2025 | 27.01.2025 | 9:00 AM- 4:00 PM
22 | Cost Center budget Report | Cost Center budget Report |  | Haile Belay/ Jai | 27.01.2025 | 27.01.2025 | 9:00 AM- 4:00 PM
23 | Profit center report | Profit center Plan/Actual |  | Haile Belay/ Jai | 27.01.2025 | 27.01.2025 | 9:00 AM- 4:00 PM

## UAT-MM
UAT PLAN-MM
Sr no | Title | Customer Engagement | From Date | To Date | Time
| UAT Workshop |  |  |  | (Ethiopia Time)
1 | Master Data- Vendor, Service, Material | Yes | 23.1.2025 | 24.1.2025 | 9:00 AM- 4:00 PM
2 | Domestic Procurement Process | Yes | 25.1.2025 | 25.1.2025 | 9:00 AM- 4:00 PM
3 | Service Procurement Process | Yes | 27.1.2025 | 27.1.2025 | 9:00 AM- 4:00 PM
4 | Import Procurement Process | Yes | 28.1.2025 | 28.1.2025 | 9:00 AM- 4:00 PM
5 | Supplier Return process with PO/Material Document | Yes | 29.1.2025 | 29.1.2025 | 9:00 AM- 4:00 PM
6 | Sub-Contracting Process | Yes | 29.1.2025 | 29.1.2025 | 9:00 AM- 4:00 PM
7 | STO Process with Delivery & Billing | Yes | 30.1.2025 | 30.1.2025 | 9:00 AM- 4:00 PM
8 | Inventory Managament--Goods Issue/Goods Transfer/Cancellation | Yes | 30.1.2025 | 30.1.2025 | 9:00 AM- 4:00 PM
9 | Physical Inventory/Stock take process | Yes | 31.1.2025 | 31.1.2025 | 9:00 AM- 4:00 PM

## UAT-FI
UAT PLAN-FI
Workshop Phase Plan - FICO
Sr no | Title | SAP S/4HANA Cloud apps name | Customer Engagement | From Date | To Date | Time
A | UAT Workshop |  |  |  |  | (Ethiopia Time)
FI-GL | General Ledger |  | Yes | 2024-01-20 | 2024-01-20 | 9:00 AM- 4:00 PM
| Master Data |  |  | 2025-01-23 | 2025-01-23
| General Ledger Master Data | Manage G/L Account Master Data | Yes
| Change General Ledger Master Data | Manage G/L Account Master Data | Yes
| Display General Ledger Master Data | Manage G/L Account Master Data | Yes
| Block/unblock General Ledger | Manage G/L Account Master Data
Yes
Business Process
| Journal Voucher - FI - Direct Expenses in FI - Provisions - Any GL to GL Postings | Post General Journal Entries | Yes
| Reverse document | Manage Journal Entries | Yes
| Clear GL Open Items | Clear Open Items Automatically | Yes
| Posting of Recurring Entries | Manage Recurring Journal Entries | Yes
| Cash Journal - Petty Expenses | Post Cash Journal Entries | Yes
| Change Document | Manage Journal Entries | Yes
| Foreign Currency Valuation Run | Perform Foreign Currency Valuation | Yes
Reporting in Accounts Receivable
| G/L Display Line items | Display Line Items in General Ledger | Yes
| G/L Display Balance | Display G/L Account Balances | Yes
| Display Cash Journal Posting | Cash Journal | Yes
| Trial Balance | Trial Balance | Yes
| Financial Statement Version | Balance Sheet/Income Statement | Yes
| Period end Closing Activities in FI | Manage Posting Period Variants | Yes
Sr no | Title | SAP S/4HANA Cloud apps name | Customer Engagement | From Date | To Date | Time
A | Business Process Understanding Workshop |  |  |  |  | (Ethiopia Time)
FI-AR | Accounts Receivable |  | Yes | 2024-01-24 | 2024-01-24 | 9:00 AM- 4:00 PM
Master Data
| Business Partner Introduction |  | Yes
| BP creation and Customer Creation | Maintain Business partner | Yes
| Customer Vendor Integration | Maintain Business partner | Yes
| Customer Account Group and Number Range |  | Yes
| Customer Doc Type |  | Yes
Business Process
| Create Customer Invoice directly in Finance | Create Outgoing Invoices | Yes
| Create Customer Invoice directly in Finance with Payment Method "C" | Create Outgoing Invoices | Yes
| Create Customer Invoice directly in Finance with Payment Method "T" and Payment Terms | Create Outgoing Invoices | Yes
| Make the Down Payment Request | Create Down Payment Request | Yes
| Post Payment Document against for Invoice and Down payment | Post Incoming Payments | Yes
| Partial payment | Create Incoming Invoices | Yes
| Clear Outgoing Payments - Manual Clearing |  | Yes
| Automatic payment for Customer | Manage automatic payments | Yes
| Create Customer invoice with Discount calculation | Create Outgoing Invoices | Yes
| Create Customer invoice with VAT rate | Create Outgoing Invoices | Yes
| Reversal of Invoice | Manage Journal Entries - New Version | Yes
Reporting in Accounts Receivable
| Display the posted document | Manage Journal Entries - New Version | Yes
| Display the posted document as per Customer | Manage Customer Line Items | Yes
| In this activity, you display the Customer balances. | Display Customer Balances | Yes
| In this activity, you display the Customer Dashboard | Accounts Receivable Overview | Yes
| In this activity, you display the Customer Outstanding amount | Monitor Overdue Receivables | Yes
| In this activity, you display the Customer Cash Balance | Cash Collection Tracker | Yes
Sr no | Title | SAP S/4HANA Cloud apps name | Customer Engagement | From Date | To Date | Time
A | Business Process Understanding Workshop |  |  |  |  | (Ethiopia Time)
FI-AP | ACCOUNTS PAYABLE |  | Yes | 2024-01-25 | 2024-01-25 | 9:00 AM- 4:00 PM
Master Data
| Business Partner Introduction |  | Yes
| BP creation and Supplier Creation | Maintain Business partner | Yes
| Customer Vendor Integration | Maintain Business partner | Yes
| Supplier Account Group and Number Range |  | Yes
| Supplier Document Type |  | Yes
Business Process
| Invoice Entry without Purchase Order | Create Incoming Invoices | Yes
| Invoice Entry without Purchase Order with Payment Method "C" | Create Incoming Invoices | Yes
| Invoice Entry without Purchase Order with Payment Method "T" and Payment Terms | Create Incoming Invoices | Yes
| Make the Down Payment Request | Create Down Payment Request | Yes
| Post Payment Document against for Invoice | Post Outgoing Payments | Yes
| Post Credit Memo | Create Incoming Invoices | Yes
| Automatic payment for Supplier | Manage automatic payments | Yes
| Clear Outgoing Payments - Manual Clearing |  | Yes
Reporting in ACCOUNTS PAYABLE
| Display the posted document | Manage Journal Entries - New Version | Yes
| Display the posted document as per Supplier | Manage Supplier Line Items | Yes
| In this activity, you display the supplier balances. | Display Supplier Balances | Yes
| In this activity, you display the supplier Dashboard | Accounts Payable Overview | Yes
| In this activity, you display the supplier Outstanding amount | Days Payable Outstanding | Yes
| In this activity, you display the supplier Cash Discount | Cash Discount Forecast | Yes
|  | Invoice Processing Analysis | Yes
|  | Invoice Processing Time | Yes
|  | Trial Balance | Yes
|  | Cash Flow Statement | Yes
|  | Display Payment Lists | Yes
Sr no | Title | SAP S/4HANA Cloud apps name | Customer Engagement | From Date | To Date | Time
A | Business Process Understanding Workshop |  |  |  |  | (Ethiopia Time)
FI-AA | Asset Accounting |  | Yes | 2025-01-27 | 2025-01-27 | 9:00 AM- 4:00 PM
Master Data
| Create Asset Master | Manage Fixed Assets | Yes
| Change Asset Master | Manage Fixed Assets | Yes
| Display Asset master | Manage Fixed Assets | Yes
Yes
Business Process
| Post Acquisition (Integrated AP) Without Purchase Order | Create Supplier Invoice - Advanced | Yes
| Post Acquisition (Integrated AP) With Purchase Order | Create Supplier Invoice - Advanced | Yes
| Create Asset Master Record for Legacy Asset (Old Asset) | Manage Legacy Assets | Yes
| Post Transfer Values for Legacy Asset | Post Transfer Values - For Legacy Asset | Yes
| Asset Post Depreciation | Schedule Asset Accounting Jobs | Yes
| Post Retirement with Customer | Post Retirement (Integrated AR) - With Customer | Yes
| Post Retirement with Revenue | Post Asset Retirement | Yes
| Post Retirement Without Revenue | Post Asset Retirement | Yes
Reporting in Accounts Receivable
| Display Asset Documents | Manage Journal Entries - New Version | Yes
| Depreciation Lists | Depreciation Lists | Yes
| Asset Balances | Asset Balances | Yes
| Asset Transactions | Asset Transactions | Yes
| Asset Values | Manage Fixed Assets | Yes
| Asset History Sheet | Asset History Sheet | Yes